{"text_format":"2","workbook":"xlsx","n_sheets":2,"sheets":["一期规划","二期规划"],"not_rendered":{"charts":0,"images":0,"macros":0,"external_links":0,"defined_names":0,"comments":0,"pivot_tables":0},"unopened":[],"bounds":{"document_bytes":16777216,"sheet_cells":100000,"run_cost":"one","rows_first":2000,"rows_last":500,"rows_between":2000,"halvings":0,"cell_chars":16384,"cell_head_chars":4096},"cells_cut":0,"cells_raw":0,"read":"whole","date_system":"1900"}

{"sheet":"一期规划","index":0,"n_rows":40,"n_cols":6,"rows_kept":40,"cut":false,"hidden":false,"merged":[[0,0,0,2],[1,0,1,2],[2,0,2,2],[3,0,3,2],[4,0,4,2],[5,0,5,2],[6,0,6,2],[7,0,7,2],[8,0,8,2],[39,0,39,2],[19,0,31,0],[19,1,26,1],[27,1,31,1],[18,3,19,3],[1,4,4,4],[9,4,17,4],[18,4,19,4],[20,4,26,4],[27,4,31,4],[32,4,35,4],[1,5,4,5],[9,5,17,5],[20,5,26,5],[27,5,31,5],[32,5,35,5],[9,0,18,1],[32,0,35,1]]}
["模块",null,null,"优先级","开发时长","备注"]
["权限管理",null,null,1,"已完成","需测试联调"]
["部门管理",null,null,1]
["角色管理",null,null,1]
["用户管理",null,null,1]
["客户管理",null,null,1,3,"作为来电和工单的基础"]
["物料管理",null,null,1,3,"作为工单的基础"]
["IVR流程",null,null,1,1,"话务优先的原则"]
["短信管理",null,null,1,"已完成","话务优先的原则"]
["话务管理",null,"通话记录",1,"已完成","需测试联调"]
[null,null,"语音留言管理",1]
[null,null,"黑名单管理",1]
[null,null,"号码归属地",1]
[null,null,"值班电话管理",1]
[null,null,"工作日管理",1]
[null,null,"工作时间管理",1]
[null,null,"坐席监控管理",1]
[null,null,"坐席组管理",1]
[null,null,"来电弹屏",1,5,"包含工单管理、客户管理、物料管理、知识库基础模块"]
["工单管理","PC工单","手制工单",null,null,"包含客户管理、物料管理；可与来电弹屏同步开发"]
[null,null,"待指派工单",1,5,"来电弹屏和手工制单为基础，需测试调整流程，以及每个流程下的操作界面"]
[null,null,"待接单工单",1]
[null,null,"待处理工单",1]
[null,null,"已处理工单",1]
[null,null,"已参与工单",1]
[null,null,"超期工单",1]
[null,null,"综合查询",1]
[null,"微信工单","微信建单",2]
[null,null,"待指派工单",2]
[null,null,"待接单工单",2]
[null,null,"待处理工单",2]
[null,null,"已处理工单",2]
["回访管理",null,"待回访工单",1,3,"配合工单模块，操作回访和完结工单"]
[null,null,"已回访工单",1]
[null,null,"待完结工单",1]
[null,null,"已完结工单",1]
["知识库","PC端",null,1,2,"配合来电弹屏"]
["报表管理",null,null,1,10,"10个报表以内，每个报表字段不超过15个"]
["大数据",null,null,1,1,"一个页面，话务类大数据公示"]
["合计",null,null,null,{"$f":"SUM(E2:E39)","v":33},"整体开发完结需3-5个工作日进行联调测试"]

{"sheet":"二期规划","index":1,"n_rows":6,"n_cols":3,"rows_kept":6,"cut":false,"hidden":false,"merged":[[0,0,0,1],[1,0,2,0]]}
["模块",null,"备注"]
["工单","微信工单","客户提交微信工单后，由客服进行审核，在此有审核操作"]
[null,"工单流程定制","工单流程指向定制"]
["知识库","微信端","知识库微信端"]
["官网对接",null,"对接官网"]
["大数据",null,"业务类大数据公示"]